## General information
Collaborative projects: general information
Lien vers l'information sur le site web INNOSQUARE
General information on collaborative projects | https://www.innosquare.com/en/nrp-application/collaborative-projects/
Procedures and regulations | https://www.innosquare.com/en/nrp-application/funding-application-pcs/
Documents and templates | https://www.innosquare.com/en/nrp-application/funding-application-pcs/
Examples of collaborative project | https://www.innosquare.com/en/completed-projects/collaborative-projects-nrp-2020-2023/
Contacts | https://www.innosquare.com/en/contact/
PC-M-E-017.02

## Checklist
Collaborative projects: checklist documents and deliverables
| Deadline | Activity | Document deliverable (templates available) | Responsible | Additional information | Status
Conception and acquisition | Date CAPE - 4 weeks | Redaction et submission of funding application | Funding application | Project leader | Template is available on INNOSQUARE website. If possible, to be sent signed to INNOSQUARE, but it is tolerated to collect partners' signatures up to 3 days before CAPE.
| Date CAPE - 4 weeks | Send Project form - Funding application to Prom FR | Project form - Funding application | INNOSQUARE
| Date CAPE - 4 weeks | Review of funding application by 2 experts | Experts' reports + email INNOSQUARE | experts / INNOSQUARE | Sent to project leader by INNOSQUARE
| Date CAPE - 2 weeks | Redaction of the funding application annex answering experts' points | Funding application Annex | Project leader | 1-2 pages maximum, to be sent to INNOSQUARE.
| Date CAPE - 3 days | Preparation of PowerPoint for presentation to CAPE | Presentation PowerPoint - funding application | Project leader + 1 industrial partner | PowerPoint template available on INNOSQUARE website. It is recommended to start preparation in advance. INNOSQUARE can support. Presentation to be sent latest 3 days before CAPE to PromFR. In some cases, Alain Lunghi will present the project to CAPE without project leader.
| Date CAPE (according to established calendar) | Presentation of funding application to CAPE | PowerPoint presentation - funding application | Project leader + 1 industrial partner | Invitation sent to project leader by PromFR (10min de presentation + 10 minutes questions). It is highly recommended to jointly present with an industrial partner.
| Date CAPE + 1 day | Feedback to funding application | Grant promise or refusal | PromFR | Communicated directly to project leader.
Realisation | Date CAPE + ≤ 3 months | Redaction and signature of consortium agreement | Consortium agreement | Project leader | Template is available. TechTransfert is available for any modifications/questions on consortium agreement.
|  | Redaction and signature of funding agreement | Funding agreement | INNOSQUARE (document creation) --> project leader (signatures collection) | INNOSQUARE prepare the contract and the project leader is responsible of collecting partner's signatures. Only once both contracts have been signed, the NRP funding (50) and partner's cash (50%) will be transferred by INNOSQUARE to project leader.
| Date Contracts signatures + ≤ 1 month | Project start (kick-off meeting) | / | Project leader | Take advantage of the kick-off meeting to align in particular on communication (internal and external to the team), plan regular project sessions and review the specific objectives of each partner to ensure they are met during the project. It is requested to communicate to INNOSQUARE the dates of project start, intermediate report and final report.
| < the 10th of each month | Issue NRP monthly progress report | NRP Monthly progress report | Project leader | Template is available on INNOSQUARE website. To be sent to INNOSQUARE before the 10th of each month from start up to project end. It is highly recommended to share this monthly report with your partners.
| Mid-project | Redaction et submission of intermediate report | Intermediate report | Project leader | Template is available on INNOSQUARE website. To be sent to INNOSQUARE.
|  | Validation of intermediate report | Attestation validation intermediate report or demand for complements | INNOSQUARE | Only once intermediate report is validated, the NRP funding (40%) and partner's cash (50%) will be transferred by INNOSQUARE to project leader.
Closure | Closure date +/- 1 month | Send and collect signatures for partner's satisfaction questionnaire | Partners' assessment form (1 completed form/partner) | Project leader | Template is available on INNOSQUARE website. To be sent to INNOSQUARE in annex of final report.
|  | Redaction and submission of final report | Final report | Project leader | Template is available on INNOSQUARE website. the final report includes in particular the results summary and the financial closure report: the detailed scientific results can be developed in a separate report put in Annex. To be sent to INNOSQUARE.
|  | Validation final report | Attestation validation final report or demand for complements | INNOSQUARE | Only once intermediate report is validated, the remaining NRP funding (10%) will be transferred by INNOSQUARE to project leader.
|  | Creation of project descriptive sheet | Project descriptive sheet | Project leader | Template is available. With INNOSQUARE support.
|  | Creation of a video capsule | Video capsule | INNOSQUARE with project leader | Template is available. With INNOSQUARE support.
|  | Creation of a scientific poster | Scientific poster | Project leader | Optional. Don't forget to put NRP and PromFR logos on all your publications.
|  | Creation of a press or scientific article | Press or scientific article | Project leader | Optional. Don't forget to put NRP and PromFR logos on all your publications.
|  | Organisation of a closure event | Closure event | Project leader | Meeting with partners, or event with external guests.
|  | Send Project form - Results to PromFR | Project form - Results | INNOSQUARE
|  | Project results presentation to the CAPE | PowerPoint presentation - project results | Project leader | Template is available on INNOSQUARE website. Invitation sent to project leader by PromFR if necessary (10min de presentation + 10 minutes questions). It is highly recommended to jointly present with an industrial partner.
|  | Project closure | / | Project leader
PC-M-E-017.02